## Product Backlog
Product Backlog: UNWelcome
SPRINT
ID | Description | 1 | 2 | 3 | 4 | 5
| Hours Needed per Sprint | 45.55 | 76 | 154.45 | 147.55 | 45.75
1 | Epic: As a player I want to improve the conveyance of the game so that players understand the game | 15.75
2 | Epic: As a developer, I want the gameplay to be more diverse and balanced so that players will enjoy playing the game. | 14.75
3 | Epic: As a developer, I want the project well organised and managed. | 15.05
Sprint 1↑ | Proof of Concept Gameplay ↑ 10/13/2017
4 | As a developer, I want enough ssets to make a game that feels complete: UI, and Character art are complete. Obstacles and Exits are functioning and complete. Sound Effects and Particles are complete. Necessary levels are completed. |  | 28.5
5 | As a player, I want a fun game to play that feels complete: Some Juice is implemented. There are minimal bugs. Gameplay is balanced. The user experience is simple and easy. |  | 15
6 | As a developer, I want a well organized project to expedite the process of working in a team: Easily understood tasks. Properly filled out SCM sheet. Effective task tracking. |  | 32.5
Sprint 2↑ | Vertical Slice ↑ 10/20/2017
7 | Epic: As a player I want a complete gameplay experience. COS: Multiple Levels with tutorials, Beautiful Art in UI, Gameplay Scene Transition, Sound and BGM Accessible Interaction, Flow Experience |  |  | 90.2
8 | Epic: As a player I want a game where I can enter flow. COS: Balanced Gameplay, Smooth Transition, JUICE |  |  | 37.5
9 | Epic: As a developer, I want a well organized project to expedite the process of working in a team. COS: Easily understood tasks. Properly filled out SCM sheet. Effective task tracking. |  |  | 26.75
Sprint 3↑ | Alpha ↑ 11/3/2017
10 | Epic: As a developer, I want to finish the game with high quality and no serious bugs. |  |  |  | 72.8
11 | Epic: As a developer, I want the project to be well organised and managed. |  |  |  | 74.75
Sprint 4↑ | Beta ↑ 11/17/2017
12 | Epic: As a developer, I want the game to be released with good quality. |  |  |  |  | 1.85
13 | Epic: As a developer, I want the game to have quality marketing materials for publishing |  |  |  |  | 7.7
14 | Epic: As a developer, I want the project to be well organised, documented, and managed. |  |  |  |  | 36.2
Sprint 5↑ | Launch ↑ 11/22/2017
| Hours Needed as a Whole | 469.3 | 423.75 | 347.75 | 193.3 | 45.75

## POCG
Sprint Backlog: Proof of Concept Gameplay |  |  |  |  | Days in Sprint
[5 empty] | 2017-10-06 | 2017-10-11 | 2017-10-12 | 2017-10-13
ID | Epic Actual Hours | Epic/Tasks | Task Actual Hours | Initials
1 | 15.75 | Epic: As a player I want to improve the conveyance of the game so that players understand the game
|  | Create Particle System For Push Demon | 3.25 | BP |  | 1 | 1.75 | 0.5
|  | Implementing the designed level | 1.25 | BP |  | 1.25
|  | Designing the demon icons | 0.5 | CL |  | 0.5
|  | Export the demon icons to the right sizes | 0.25 | CL |  | 0.25
|  | Designing the neighbor characters | 3.25 | CL |  | 2 | 1.25
|  | Implement camera control feature - swipe | 1 | ER |  | 1
|  | Implement camera control feature - Zoom In/Out | 0.25 | ER |  | 0.25
|  | Implementing Art Assets | 0.5 | BP |  |  | 0.5
|  | Implementing Range Indicator | 1.5 | ER |  |  | 1.5
|  | Design environment art assets | 3.5 | CL |  |  | 1.5 | 2
|  | Update help text | 0.25 | BP |  |  |  | 0.25
|  | Create the readme.txt file for submisstion | 0.25 | BP |  |  |  | 0.25
2 | 14.75 | Epic: As a developer, I want the gameplay to be more diverse and balanced so that players will enjoy playing the game.
|  | Design new game layouts | 1 | BP |  | 1
|  | Implementing the pull demon | 1.5 | ER |  | 1.5
|  | Design UI Framework | 1 | BH |  | 1
|  | Implement UI Framework on Axure | 1.75 | BH |  | 1.75
|  | Testing the new level | 0.5 | BP |  |  | 0.5
|  | Implementing feature - multiple entries for neighbors | 1.75 | ER |  |  | 1.75
|  | Balacing the gameplay and testing | 1.25 | BH |  |  | 1.25
|  | Polish the levels | 1 | BH |  |  | 0.5 | 0.5
|  | Testing and debugging | 1 | BH |  |  | 1
|  | Testing the debugging | 1.5 | BP |  |  |  | 1.5
|  | Integration testing | 2.5 | ER |  |  |  | 2.5
3 | 15.05 | Epic: As a developer, I want the project well organised and managed.
|  | Scrum Meeting | 1.8 | BP, ER, LC, BH |  | 0.15 * 4 | 0.15 * 4 | 0.15 * 4
|  | Spring Planning | 8 | BP, ER, LC, BH | 2*4
|  | Lecture | 4 | BP, ER, LC, BH | 1*4
|  | Update GDD Mindmup | 1 | BP, ER, LC, BH |  |  |  | 0.25*4
|  | Update SCM document | 0.25 | BH |  |  |  | 0.25
[6 empty] | 11.5 | 11.5 | 7.75

## VS
Sprint Backlog: Vertical Slice |  |  |  |  | Days in Sprint
[5 empty] | 2017-10-16 | 2017-10-17 | 2017-10-18 | 2017-10-19 | 2017-10-20
ID | Epic Actual Hours | Epic/Tasks | Task Actual Hours | Initials
4 | 28.5 | As a developer, I want enough ssets to make a game that feels complete: UI, and Character art are complete. Obstacles and Exits are functioning and complete. Sound Effects and Particles are complete. Necessary levels are completed.
|  | Design and Refine the Push demon icon - Completed by Lexi (Artist) | 2 | LC |  | 2
|  | Design and Refine the Spring demon icon - Completed by Lexi (Artist) | 2 | LC |  |  | 2
|  | Design and Refine the Pull demon icon - Completed by Lexi (Artist) | 2 | LC |  |  |  | 2
|  | Complete UI Icons for side panel - Completed by Lexi (Artist) | 2 | LC |  |  |  |  | 2
|  | Implement side panel functionality - Completed by Emily (Programming) | 1 | ER |  |  | 1
|  | Polish the Vertical Slice level art - Completed by Clayton (Artist) | 6 | CD |  |  |  | 3 | 3
|  | Create dialog box art - Completed by Clayton (Artist) | 2 | CD |  |  | 2
|  | Design Tutorial Level - Completed by Blake (Designer) | 3 | BP |  |  | 3
|  | Implement new background art and new obstacle art into VS level - Completed by Blake (Designer) | 2 | BP |  |  |  |  | 2
|  | Implement floor tile art - Completed by Blake (Designer) | 1 | BP |  |  |  |  | 1
|  | Find sound effects to use for demon firing and button pressing - Completed by Bryan (Designer/Producer) | 1 | BH |  |  |  | 1
|  | Implement the Demon animations - Completed by Bryan (Designer/Producer) | 2.5 | BH |  |  |  |  | 2.5
|  | Create paper prototype for new level - Completed by Bryan (Designer/Producer) | 1 | BH |  | 1
|  | Implement new level in the game - Completed by Bryan (Designer/Producer) | 1 | BH |  | 1
5 | 15 | As a player, I want a fun game to play that feels complete: Some Juice is implemented. There are minimal bugs. Gameplay is balanced. The user experience is simple and easy.
|  | Clarify turn structure - Completed by Emily (Programming) | 1 | ER |  | 1
|  | Fixed Demon not reloading bug - Completed by Emily (Programming) | 1 | ER |  |  |  | 1
|  | Bug fixes - completed by Emily (Programming) | 3 | ER |  |  | 3
|  | Create firing particles for demons - Completed by Blake (Design) | 3 | BP |  | 3
|  | Test new art that has been implemented so far - Completed by Blake (Design) | 2 | BP |  |  |  | 2
|  | Perform integration testing for content put in this week - Completed by All Team Members | 5 | LC, CD, ER, BH, BP |  |  |  |  | 1 x 5 (each member)
6 | 32.5 | As a developer, I want a well organized project to expedite the process of working in a team: Easily understood tasks. Properly filled out SCM sheet. Effective task tracking.
|  | Sprint Review Report - Completed by All Team Members | 4 | LC, CD, ER, BH, BP | 1 x 4 (each member)
|  | Scrum Meetings - Completed by all Team Members | 5 | LC, CD, ER, BH, BP | .15 x 4 (each member) | .12 x 5 (each member) | .12 x 5 (each member) | .12 x 5 (each member) | .12 x 5 (each member)
|  | Sprint Planning - Completed by all Team Members | 9 | LC, CD, ER, BH, BP | 1 x 4 (each member) | 1x5 (each member)
|  | Sprint Retrospective Meeting - Completed by all Team members | 4 | LC, CD, ER, BH, BP | 1 x 4 (each member)
|  | Sprint Review/Kleenex Testing - Completed by all team members | 4 | LC, CD, ER, BH, BP | 1 x 4 (each member)
|  | Onbarding Training (Teaching) - Completed by Lexi (Artist) | 2 | LC |  | 2
|  | Onboarding Training (Learning) - Completed by Clayton (Artist) | 2 | CD |  | 2
|  | Update the GDD - Completed by Blake (Designer) | 1 | BP | 1
|  | Update the GDD - Completed by Bryan (Designer/Producer) | 1 | BH | 1
|  | Update the SCM sheet - Completed by Bryan (Designer/Producer) | 0.5 | BH |  |  |  |  | 0.5
[5 empty] | 12.6 | 17.6 | 11.6 | 9.6 | 11.6
Note on F27: Only 4 members on the team at this time -Blake Philley
Note on G29: Due to integrating a new team member, planning had to be done twice. -Blake Philley
Note on F30: Only 4 members on the team at this time -Blake Philley
Note on F31: Only 4 members on the team at this time -Blake Philley

## Alpha
Sprint Backlog: Alpha |  |  |  |  | Days in Sprint
[5 empty] | 2017-10-23 | 2017-10-24 | 2017-10-25 | 2017-10-26 | 2017-10-27 | 2017-10-30 | 2017-10-31 | 2017-11-01 | 2017-11-02 | 2017-11-03
ID | Epic Actual Hours | Epic/Tasks | Task Actual Hours | Initials | bar: 2017-10-23
7 | 90.2 | Epic: As a player I want a complete gameplay experience. COS: Multiple Levels with tutorials, Beautiful Art in UI, Gameplay Scene Transition, Sound and BGM Accessible Interaction, Flow Experience
|  | Create 6 new neighbor icons - Completed by Lexi (Artist) | 3 | LC | 2017-10-24: 3
|  | Animate main neighbor - Completed by Lexi (Artist) | 1.5 | LC | 2017-10-25: 1.5
|  | Begin animating other neighbors - Completed by Lexi (Artist) | 1.5 | LC | 2017-10-25: 1.5
|  | Touch up main neighbor animation - Completed by Lexi (Artist) | 1 | LC | bar: 2017-10-26
|  | Continue on other neighbor animations - Completed by Lexi (Artist) | 1.5 | LC | 2017-10-26: 1.5
|  | Continue on other neighbor animations - Completed by Lexi (Artist) | 2.75 | LC | 2017-10-27: 2.75
|  | Finish other neighbor animations - Completed by Lexi (Artist) | 2.5 | LC | 2017-10-30: 2.5
|  | Complete other needed UI buttons - Completed by Lexi (Artist) | 1 | LC | bar: 2017-10-31
|  | Refine health bar art - Completed by Lexi (Artist) | 0.25 | LC | 2017-10-31: 0.25
|  | Create more UI buttons - Completed by Lexi (Artist) | 2.75 | LC | 2017-11-01: 2.75
|  | Create Win/Lose Screen art - Completed by Lexi (Artist) | 2.75 | LC | 2017-11-02: 2.75
|  | Finish main menu UI buttons - Completed by Lexi (Artist) | 1.75 | LC | 2017-11-03: 3
|  | Fix crystal ball art conveyance - Completed by Clayton (Artist) | 0.2 | CD | 2017-10-24: 0.2
|  | Refine Environment tiles conveyance - Completed by Clayton (Artist) | 2.5 | CD | 2017-10-24: 2.5
|  | Add rendering to neighbor art - Completed by Clayton (Artist) | 3 | CD | 2017-10-25: 3
|  | Finish rendering on neighbor art - Completed by Clayton (Artist) | 5 | CD | 2017-10-26: 5
|  | Compositing on Tutorial 1 | 3 | CD | 2017-10-27: 3
|  | Fix colors on portal | 2.5 | CD | 2017-10-27: 2.5
|  | Polish and rendering obstacle art - Completed by Clayton (Artist) | 2.5 | CD | 2017-10-30: 2.5
|  | Create level background art - Completed by Clayton (Artist) | 2.75 | CD | 2017-10-31: 2.75
|  | Continue creating background art - Completed by Clayton (Artist) | 4.75 | CD | 2017-11-01: 2.75; 2017-11-03: 2
|  | Create animations for exits - Completed by Clayton (Artist) | 2 | CD | 2017-11-02: 2
|  | Design UI for side panel - Completed by Clayton (Artist) | 0.75 | CD | 2017-11-02: 0.75
|  | Finish animations for exits - Completed by Clayton (Artist) | 1 | CD | bar: 2017-11-03
|  | Implement Wall tiles - Completed by Emily (Programminng) | 0.25 | ER | 2017-10-24: 0.25
|  | Fix pull demon functionality - Completed by Emily (Programming) | 1 | ER | bar: 2017-10-24
|  | Implement new UI functionality - Completed by Emily (Programming) | 2.5 | ER | 2017-10-24: 2.5
|  | Restrict player's actions during turns - Completed by Emily (Programming) | 0.5 | ER | 2017-10-30: 0.5
|  | Create auto-play toggle functionality - Completed by Emily (Programming) | 0.25 | ER | 2017-10-31: 0.5
|  | Implement side panel UI - Completed by Emily (Programming) | 2 | ER | 2017-10-30: 2
|  | Add range indicators for neighbors - Completed by Emily (Programming) | 1 | ER | bar: 2017-11-01
|  | Implemented demon summoning animation - Completed by Emily (Programming) | 1.75 | ER | 2017-11-02: 1.75
|  | Design levels on paper - Completed by Blake (LD) | 2 | BP | 2017-10-24: 2
|  | Implement 2nd tutorial level - Completed by Blake (LD) | 3.5 | BP | 2017-10-25: 2; 2017-10-26: 1.5
|  | Implement environment art - Completed by Blake (LD) | 2.75 | BP | 2017-10-25: 0.75; 2017-10-26: 1; 2017-10-27: 1
|  | Implement level art - Completed by Blake (LD) | 5.75 | BP | 2017-10-31: 1.25; 2017-11-02: 1.5; 2017-11-03: 3
|  | Design levels on paper - Completed by Bryan (LD/Producer) | 2 | BH | 2017-10-24: 2
|  | Implement new levels - Completed by Bryan (LD/Producer) | 2 | BH | 2017-10-25: 2
|  | Design new enemy - Completed by Bryan (LD/Producer) | 0.75 | BH | 2017-10-25: 0.75
|  | Implement level select screen - Completed by Bryan (LD/Producer) | 1.5 | BH | 2017-10-26: 1.5
|  | Implement sound - Completed by Bryan (LD/Producer) | 0.5 | BH | 2017-10-27: 0.5
|  | Bug fixing in menus - Completed by Bryan (LD/Producer) | 1 | BH | bar: 2017-10-27
|  | Implement demon summoning animation - Completed by Bryan (LD/Producer) | 2.75 | BH | 2017-11-01: 2.25; 2017-11-02: 0.5
|  | Implement UI Art assets - Completed by Bryan(LD/Producer) | 4.25 | BH | 2017-11-02: 2.25; 2017-11-03: 2
8 | 37.5 | Epic: As a player I want a game where I can enter flow. COS: Balanced Gameplay, Smooth Transition, JUICE
|  | Review Paper Level Design - Completed by Blake (LD) | 0.75 | BP | 2017-10-24: 0.75
|  | Review Paper Level Design - Completed by Bryan (LD/Producer) | 0.75 | BH | 2017-10-24: 0.75
|  | Refine Sounds - Completed by Bryan (LD/Producer) | 1.5 | BH | 2017-10-26: 1; 2017-11-01: 0.5
|  | Tutorial refinement - Completed by Blake (LD) | 4.75 | BP | 2017-10-27: 0.75; 2017-10-30: 2.5; 2017-10-31: 1.5
|  | Playtesting with other team - Completed by Blake | 1 | BP | bar: 2017-10-27
|  | Playtesting with other team - Completed by Emily | 1 | ER | bar: 2017-10-27
|  | Playtesting with other team - Completed by Bryan | 1 | BH | bar: 2017-10-27
|  | Improving menu funcitonality - Completed by Bryan (LD/Producer) | 2 | BH | 2017-10-31: 2
|  | Testing new levels - Completed by Bryan (LD/Producer) | 2.75 | BH | 2017-10-30: 2; 2017-10-31: 0.75
|  | Fix performance issue caused by tile rendering - Completed by Emily (Programming) | 1.25 | ER | 2017-10-31: 1.25
|  | Refine demon targeting based on testing feedback - Completed by Emily (Programming) | 1 | ER
|  | Refine Health bar sprite - completed by Lexi (Art) | 0.5 | LC | 2017-10-31: 0.5
|  | Script revision on tutorial - Completed by Blake (LD) | 1 | BP | bar: 2017-11-02
|  | Loading Screen Splash - Completed by Emily (Programming) | 0.5 | ER | 2017-11-03: 0.5
|  | Improve Demon Summoning UI - Completed by Emily (Programming) | 2 | ER | 2017-10-25: 2
|  | Improve tutorial fucntionality and fix bugs - Completed by Emily (Programming) | 1 | ER | bar: 2017-10-31
|  | Implemented exit animation - completed by Emily (Programming) | 0.75 | ER | 2017-11-03: 0.75
|  | Playtesting - Completed by Emily (Programming) | 0.75 | ER | 2017-11-03: 0.75
|  | Playtesting - Completed by Lexi (Art) | 1.75 | LC | 2017-11-03: 1.75
|  | Playtesting - Completed by Clayton (Art) | 1.75 | CD | 2017-11-03: 1.75
|  | Playtesting - completed by Bryan (LD/Producer) | 1.75 | BH | 2017-11-03: 1.75
|  | Playtesting - completed by Blake (LD/Producer) | 1.75 | BP | 2017-11-03: 1.75
|  | Bug fixing - Completed by Emily (Programming) | 2.5 | ER | 2017-11-02: 1; 2017-11-03: 1.5
|  | Integration testing - Completed by Emily (Programming) | 3.75 | ER | 2017-10-26: 1.5; 2017-10-27: 1.25; 2017-11-03: 1
9 | 26.75 | Epic: As a developer, I want a well organized project to expedite the process of working in a team. COS: Easily understood tasks. Properly filled out SCM sheet. Effective task tracking.
|  | Sprint Review - All Members | 3.75 | CD, BH, ER, LC, BP | 2017-10-23: .75 x 5 ( each member)
|  | Sprint Retrospective - All Members | 2.5 | CD, BH, ER, LC, BP | 2017-10-23: .5 x 5 ( each member)
|  | Sprint Planning - All Members | 5 | CD, BH, ER, LC, BP | 2017-10-23: 1 x 5 ( each member)
|  | Kleenex Testing - All Members | 3.75 | CD, BH, ER, LC, BP | 2017-10-23: .75 x 5 ( each member)
|  | Scrum Meeting - All Members | 11.25 | CD, BH, ER, LC, BP |  | .25 x 5 (each member) | .25 x 5 (each member) | .25 x 5 (each member) | .25 x 5 (each member) | .25 x 5 (each member) | .25 x 5 (each member) | .25 x 5 (each member) | .25 x 5 (each member) | .25 x 5 (each member)
|  | Organize file structure | 0.5 | BP | 2017-11-02: 0.5

## Beta
Sprint Backlog: Beta |  |  |  |  | Days in Sprint
[5 empty] | 2017-11-06 | 2017-11-07 | 2017-11-08 | 2017-11-09 | 2017-11-10 | 2017-11-13 | 2017-11-14 | 2017-11-15 | 2017-11-16 | 2017-11-17
ID | Epic Actual Hours | Epic/Tasks | Task Actual Hours | Initials | bar: 2017-11-06
10 | 72.8 | Epic: As a developer, I want to finish the game with high quality and no serious bugs.
|  | Testing and Bug Fixing (LD/Producer) | 3.35 | BP | 2017-11-07: 1.5; 2017-11-10: 1.85
|  | Testing with other teams | 3.85 | BP | 2017-11-08: 2.85; 2017-11-10: 1
|  | Update GDD | 1 | BP | bar: 2017-11-09
|  | Create Survey (LD) | 0.5 | BP | 2017-11-09: 0.5
|  | Survey test and refine (LD) | 0.5 | BP | 2017-11-09: 0.5
|  | Usability Report (LD) | 2.85 | BP | 2017-11-15: 2.85
|  | Redesign the Tutorial and Implement (LD) | 1.85 | BP | 2017-11-16: 1.85
|  | Testing and Bug Fixing (LD/Producer) | 1.5 | BH | 2017-11-07: 1.5
|  | Testing with other teams (LD/Producer) | 2 | BH | 2017-11-08: 2
|  | Updating testing report (LD/Producer) | 3.7 | BH | 2017-11-08: 0.85; 2017-11-09: 2.85
|  | Usability Report (LD/Producer) | 5.7 | BH | 2017-11-10: 2.85; 2017-11-15: 2.85
|  | Implementing the new UI (LD/Producer) | 1.85 | BH | 2017-11-16: 1.85
|  | UI Asset Design (Artist) | 1.5 | LC | 2017-11-07: 1.5
|  | UI -Character Animation (Artist) | 4.7 | LC | 2017-11-08: 3; 2017-11-09: 0.85; 2017-11-10: 0.85
|  | Flyers and Posters for Beta Playtest (Artist) | 4 | LC | 2017-11-09: 2; 2017-11-10: 2
|  | Refine the UI and tiles assets (Artist) | 2.85 | LC | 2017-11-15: 2.85
|  | Refine UI and animation (Artist) | 1.85 | LC | 2017-11-16: 1.85
|  | UI Asset Design (Artist) | 1.5 | CD | 2017-11-07: 1.5
|  | UI Reworks (Artist) | 0.85 | CD | 2017-11-08: 0.85
|  | Level Design Blockouts- Redesign and refinement- All levels (Artist) | 8 | CD | 2017-11-08: 2; 2017-11-09: 3; 2017-11-10: 3
|  | Refine the UI and tiles assets (Artist) | 2.85 | CD | 2017-11-15: 2.85
|  | Designing tutorial 3 Environment (Artist) | 1.85 | CD | 2017-11-16: 1.85
|  | Testing and Bug Fixing (Programing) | 3.35 | ER | 2017-11-07: 1.5; 2017-11-16: 1.85
|  | Fix the tutorial (Programming) | 5 | ER | 2017-11-08: 2; 2017-11-09: 3
|  | Refactoring tower shooting (Programming) | 3 | ER | 2017-11-10: 3
|  | Usability Report (Programming) | 2.85 | ER | 2017-11-15: 2.85
11 | 74.75 | Epic: As a developer, I want the project to be well organised and managed.
|  | Kleenex Testing (production task-All Members) | 5 | BP, LC, ER, BH, CD | 2017-11-06: 1x 5 ( per member)
|  | Sprint Retrospective (production task-All Members) | 5 | BP, LC, ER, BH, CD | 2017-11-06: 1x 5 ( per member)
|  | Sprint Planning (production task-All Members) | 5 | BP, LC, ER, BH, CD | 2017-11-06: 1x 5 ( per member)
|  | Lecture (All team members) | 21.5 | BP, LC, ER, BH, CD | 2017-11-07: 1.5x 5 (per member); 2017-11-14: 1x 4 (BP_ABs); 2017-11-16: 1x 5 (per member); 2017-11-17: 1x 5 (per member)
|  | Scrum meeting (All team members) | 6 | BP, LC, ER, BH, CD |  | 0.15x 5 (per member) | 0.15x 5 (per member) | 0.15x 5 (per member) | 0.15x 5 (per member) |  | 0.15x 5 (per member) | 0.15x 5 (per member) | 0.15x 5 (per member) | 0.15x 5 (per member)
|  | Testing on main Campus (All team members) | 15 | BP, LC, ER, BH, CD | 2017-11-13: 3x 5 (per member)
|  | Discussing the feedback and plan for the next milestone (All team members) | 8 | LC, ER, BH, CD | 2017-11-14: 2x 4 (BP_ABs)
|  | Testing and bug fixing (All team members) | 9.25 | BP, LC, ER, BH, CD | 2017-11-17: 1.85x 5
[5 empty] | 15 | 15.75 | 14.3 | 14.45 | 15.3 | 15 | 12.75 | 15 | 15 | 15.33

## Launch
Sprint Backlog: Launch |  |  |  |  | Days in Sprint - Hours worked
[5 empty] | 2017-11-20 | 2017-11-21 | 2017-11-22
ID | Epic Actual Hours | Epic/Tasks | Task Actual Hours | Initials
12 | 1.85 | Epic: As a developer, I want the game to be released with good quality.
|  | Bug Fixing - Emily (Programmer) | 1.85 | ER |  | 1.85
13 | 7.7 | Epic: As a developer, I want the game to have quality marketing materials for publishing
|  | Creating DVD Cover and Poster - Clayton (Artist) | 3.85 | CD |  | 1.85 | 2
|  | Trailer | 3.85 | LC |  | 1.85 | 2
14 | 36.2 | Epic: As a developer, I want the project to be well organised, documented, and managed.
|  | Scrum Meeting - All members | 2.25 | CD, BH, ER, LC, BP | 0.15 x 5 (each member) | 0.15 x 5 (each member) | 0.15 x 5 (each member)
|  | Lecture - All members | 5 | CD, BH, ER, LC, BP |  | 1 x 5 (each)
|  | Sprint Retrospective - All Members | 5 | CD, BH, ER, LC, BP | 1 x 5 ( each member)
|  | Sprint Planning - All Members | 5 | CD, BH, ER, LC, BP | 1 x 5 ( each member)
|  | Usability Testing - All Members | 5 | CD, BH, ER, LC, BP | 1 x 5 ( each member)
|  | Writing GDD - Bryan (LD/Production) | 4.7 | BH |  | 1.85 | 2.85
|  | Writing GDD - Emily (Programmer) | 2.85 | ER |  |  | 2.85
|  | Writing GDD - Blake (LD) | 4.7 | BP |  | 1.85 | 2.85
|  | Writing GDD - Clayton (Art) | 0.85 | CD |  |  | 0.85
|  | Writing GDD - Lexi (Art) | 0.85 | LC |  |  | 0.85